## Project Tracker - New
Phase | Module | Description | Task | Deliverables | Status | Start Date | Target Date
1 | Requirements Understanding | Understand business problem, architecture, datasets, personas | Analyze project requirements, identify stakeholders, define use cases, study available datasets, document functional and non-functional requirements, define user personas and workflows | Requirement understanding document | Done | 2026-06-11 | 2026-06-12
2 | Solution Architecture | Create architecture diagrams, agent workflow, deployment design | Design system architecture, agent workflow, data flow, and deployment structure | Architecture breakdown document | Done | 2026-06-11 | 2026-06-12
3 | Project Setup & Planning | Setup project structure, Git, VS Code environment | Create repository, virtual environment, architecture design | Project Structure, HLD | Done | 2026-06-12 | 2026-06-12
5 | Document Ingestion Pipeline | Load healthcare documents | PDF, DOCX, TXT ingestion | Document Loader Module | Done | 2026-06-13 | 2026-06-19
6 | Text Processing & Chunking | Prepare documents for embedding | Cleaning, chunking | Chunked Documents | Done | 2026-06-13 | 2026-06-19
7 | Embedding Pipeline | Generate vector embeddings | Embedding generation | Embedding Store | Done | 2026-06-13 | 2026-06-19
8 | Vector DB Comparison | Create a comparison document for vectordb selection and upload it on github: Indexing algo, Search (keyword search, vector search, hybrid search), data scale (<1 M vectors) | ChromaDB, Pinecone, weaviate, FAISS | Github link with updated docs | Done | 2026-06-19 | 2026-06-19
9 | Vector Database Setup | Store embeddings | FAISS indexing | Vector Database | Done | 2026-06-13 | 2026-06-19
10 | Enterprise RAG Pipeline | Implement semantic retrieval | Similarity search, citations | RAG Engine | Done | 2026-06-13 | 2026-06-19
11 | Streamlit Frontend | Build chatbot UI | Chat interface, file uploads | Streamlit App | Done | 2026-06-13 | 2026-06-19
12 | FastAPI Backend | Build backend APIs | Chat APIs, upload APIs | Backend Services | Done | 2026-06-13 | 2026-06-19
13 | MCP Tool Development | Create healthcare data tools | Patient, appointment, billing tools | MCP Tool Registry | Done | 2026-06-20 | 2026-06-29
14 | Planner Agent | Break complex queries into tasks | Task decomposition | Planner Agent | Done
15 | Retriever Agent | Retrieve enterprise documents | Document retrieval | Retriever Agent | Done
16 | MCP Agent | Query structured data | Tool calling | MCP Agent | Done
17 | Multimodal Agent | Process images and reports | OCR and image understanding | Multimodal Agent | Done
18 | Reasoning Agent | Generate final responses | LLM reasoning | Reasoning Agent | Done
19 | Agent Orchestration | Connect all agents | LangGraph workflow | Agent Workflow | Done
20 | File Upload APIs | Upload documents and images | Upload endpoints | Upload Service | Done | 2026-06-30 | 2026-07-03
21 | Dashboard Development | Display metrics and traces | Analytics dashboard | Dashboard | Done
22 | Evaluation Framework | Evaluate RAG quality | Faithfulness, relevance checks | Evaluation Report | Done
23 | Guardrails & Security | Secure AI workflows | PHI masking, prompt protection | Security Layer | Done
24 | Observability & Logging | Monitor workflows | Tracing and logs | Monitoring Dashboard | Done
25 | Unit Testing | Validate modules | Test development | Unit Test Report | Done | 2026-07-03 | 2026-07-11
26 | Integration Testing | Validate end-to-end workflows | System testing | Integration Report | Done
27 | Performance Testing | Measure scalability | Load testing | Performance Report | Done
28 | Dockerization | Containerize solution | Docker image creation | Docker Images | Done
29 | Azure Deployment | Deploy solution to Azure | Container deployment | Live Application | Done
30 | Documentation & Demo | Create documentation and final demo | User guide, architecture docs | Technical Documentation, Demo | Done